## Dashboard
SentriFlow 7-Day Plan: Dashboard
Day 1 = 20 Oct 2026 ¦ Day 7 = 26 Oct 2026
Overall
Total tasks | Done | In progress | Blocked | Not started | Overdue | Est. hours | Progress (hours-weighted)
36 | 0 | 0 | 0 | 36 | 33 | 152 | 0%
By workstream
Workstream | Tasks | Done | In progress | Blocked | Est. hours | Progress (hours-weighted)
Software | 21 | 0 | 0 | 0 | 95 | 0%
Proposal | 15 | 0 | 0 | 0 | 57 | 0%
Workload by owner (primary owner only)
Role | Name | Tasks | Est. hours | Capacity (h) | Load | Progress (hours-weighted)
R1 | Marcel Luther Sitorus | 11 | 38 | 42 | 90.48% | 0%
R2 | Audric Yusuf Maynard Simatupang | 8 | 38 | 42 | 90.48% | 0%
R3 | Mahatma Brahmana | 9 | 37 | 42 | 88.1% | 0%
R4 | Ishak Palentino Napitupulu | 8 | 39 | 42 | 92.86% | 0%
Load above 100% (red) means the owner has more estimated hours than available capacity.
By day
Day | Date | Tasks due | Done (of due) | Tasks active | Software milestone | Proposal milestone
D1 | 2026-10-20 | 3 | 0 | 5 | Platform decided; repo ready; proxy intercepting HTTPS in a browser | Outline, owners and page budget set; survey launched; cover fixed
D2 | 2026-10-21 | 5 | 0 | 10 | Flow capture, process attribution, DB schema; API contract frozen | Introduction and root-cause analysis drafted
D3 | 2026-10-22 | 6 | 0 | 11 | Backend REST + WebSocket live; blocklist and PII inspector working; frontend running on mock data | Existing-solutions comparison and Proposed Solution drafted; diagrams started
D4 | 2026-10-23 | 4 | 0 | 8 | CHECKPOINT: Halt hold/release works end to end; live dashboard on real data | Survey closed; diagrams and Technical Implementation drafted
D5 | 2026-10-24 | 8 | 0 | 11 | Halt prompt UI, alerts, privacy score, pinning/QUIC handling; tests running | Expected MVP/impact/plan done; survey results integrated; references checked
D6 | 2026-10-25 | 7 | 0 | 7 | Integration and bug fixing; geo-map/anomaly only if on track | Full draft assembled (max 15 pages); peer review against rubric
D7 | 2026-10-26 | 3 | 0 | 3 | KPI measurement, rehearsal, backup video, code freeze | Final fixes; export FPH_Senklok.pdf; submit
Notes: milestones are my proposed targets. Overdue uses today's date and the Day 1 date in Setup.

## Tasks
SentriFlow 7-Day Task Tracker: Software MVP + Full Proposal (Team Senklok)
Edit Status (column O) and Notes (column R). Owner name, dates, % done and Gantt are formulas.
[15 empty] | Gantt: |  | blue=Software, orange=Proposal, green=Done | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26
ID | Workstream | Task | Description | Definition of done | Owner role | Owner | Support | Start day | Due day | Start date | Due date | Priority | Est. hours | Status | % done | Depends on | Notes | D1 | D2 | D3 | D4 | D5 | D6 | D7
S01 | Software | Platform decision & dev environment | Choose the primary OS (Windows 11 recommended, as in the concept proposal) and fix it for the whole build. Create Git repo, Python venv, Node setup, folders (proxy/, backend/, frontend/, tests/), linters and README. | Decision recorded; all 4 members can clone and run the hello-world proxy | R2 | Audric Yusuf Maynard Simatupang | R1 | 1 | 1 | 2026-10-20 | 2026-10-20 | Core | 3 | Done | 0% |  | 2026-10-27 (Asia/Jakarta): Implemented Windows 11 / Python 3.12 / Node 22 environment, setup/run/test/build scripts and README. Local Linux environment validated; teammates should run setup on Windows. See docs/audric-worklog.md. | ■
S02 | Software | Proxy pipeline + local CA | Run mitmproxy with an addon on 127.0.0.1. Install the local CA with user consent. Route system HTTP/HTTPS via the proxy and restore settings automatically on exit. | Open an HTTPS site in a browser and see the decrypted request logged; proxy settings restored after stop | R2 | Audric Yusuf Maynard Simatupang | R3 | 1 | 2 | 2026-10-20 | 2026-10-21 | Core | 6 | In progress | 0% | S01 | 2026-10-27 (Asia/Jakarta): Implemented embedded proxy, per-install CA lifecycle, consent, exact proxy snapshot/restore and crash watchdog. Real local HTTP/HTTPS tests pass. Native Windows CA/browser and forced-termination recovery evidence pending. | ■ | ■
S03 | Software | Flow capture & event model | Extract host, URL, method, headers, body size and timestamps from each flow. Define one JSON event schema shared by backend and frontend. | Schema document + addon emits events for every flow | R2 | Audric Yusuf Maynard Simatupang | R4 | 2 | 2 | 2026-10-21 | 2026-10-21 | Core | 3 | Done | 0% | S02 | 2026-10-27 (Asia/Jakarta): Implemented masked flow capture, event envelope, bounded event bus and matching TypeScript contracts. Lifecycle events verified; contract frozen in docs/api.md. |  | ■
S04 | Software | Process attribution (psutil) | Map client source port to PID and executable name. Handle unknown or short-lived processes. | At least 90% of captured flows in a test session carry a process name | R3 | Mahatma Brahmana | R2 | 2 | 2 | 2026-10-21 | 2026-10-21 | Core | 4 | Not started | 0% | S02 |  |  | ■
S05 | Software | SQLite schema & data layer | Tables for flows, rules, alerts, blocklist, settings. Data-access functions, masked logging (labels and masked samples only, no full payloads). | Schema applied; CRUD functions covered by tests | R3 | Mahatma Brahmana | R2 | 2 | 2 | 2026-10-21 | 2026-10-21 | Core | 4 | Not started | 0% | S01 |  |  | ■
S06 | Software | FastAPI backend: REST + WebSocket | Endpoints for flows, rules, alerts, settings and Allow/Block decisions. WebSocket pushes live events. Bind to 127.0.0.1 only, session token and origin check. Freeze the API contract by end of Day 2 so the frontend can mock against it. | API contract doc shared; live events reach a WebSocket test client | R2 | Audric Yusuf Maynard Simatupang | R4 | 2 | 3 | 2026-10-21 | 2026-10-22 | Core | 7 | Done | 0% | S03, S05 | 2026-10-27 (Asia/Jakarta): Implemented loopback REST, authenticated WebSocket/Halt commands, CRUD/history/settings, Host/Origin/token checks, TS clients and Vite proxy. API/WS integration tests pass. |  | ■ | ■
S07 | Software | Tracker blocklist loader & matcher | Load StevenBlack hosts / EasyPrivacy into SQLite and match request destinations (including subdomains). Option: alert or auto-block. | Known tracker domains matched in a test list; unknown domain not matched | R3 | Mahatma Brahmana |  | 3 | 3 | 2026-10-22 | 2026-10-22 | Core | 3 | Not started | 0% | S05 |  |  |  | ■
S08 | Software | PII & sensitive-string inspector | Scan URL, headers and body for email, phone, card numbers (Luhn) and user-defined strings. Size and content-type limits. Return pattern label plus masked sample. | Unit tests pass; 100% of seeded dummy PII detected | R3 | Mahatma Brahmana | R2 | 3 | 3 | 2026-10-22 | 2026-10-22 | Core | 6 | Not started | 0% | S03 |  |  |  | ■
S09 | Software | Decision engine & Halt (hold/release) | Trigger Halt when an unknown process sends a large payload, PII is found or a tracker is contacted. Hold the flow until the user decides or timeout (default Block). Rules once/always with precedence, saved in SQLite. | Held request released or dropped by decision; decision applied within 1 second | R2 | Audric Yusuf Maynard Simatupang | R3 | 3 | 4 | 2026-10-22 | 2026-10-23 | Core | 8 | Done | 0% | S04, S06, S07, S08 | 2026-10-27 (Asia/Jakarta): Implemented independent Halt futures, all four choices, persistent scoped rules and precedence, timeout/shutdown Block and persistence before release. Concurrency and persistence failure tests pass. |  |  | ■ | ■
S10 | Software | Frontend scaffold & WebSocket client | React + Tailwind project, routing, layout, WebSocket hook. Build against mock data from the API contract so work does not wait for the backend. | Dashboard shell renders mock events | R4 | Ishak Palentino Napitupulu |  | 2 | 3 | 2026-10-21 | 2026-10-22 | Core | 4 | Not started | 0% | S01 |  |  | ■ | ■
S11 | Software | Live traffic dashboard | Connections grouped by application, live upload/download speed (Recharts), filterable flow table, plain-language labels. | Real events from the backend show up live, grouped per app | R4 | Ishak Palentino Napitupulu | R2 | 3 | 4 | 2026-10-22 | 2026-10-23 | Core | 7 | Not started | 0% | S06, S10 |  |  |  | ■ | ■
S12 | Software | Halt prompt UI & rules page | Modal showing process, destination, matched pattern and size. Allow/Block once or always, countdown to default Block, desktop notification fallback. Rules list with edit/delete. | Prompt appears on a held request and the decision reaches the backend | R4 | Ishak Palentino Napitupulu | R2 | 4 | 5 | 2026-10-23 | 2026-10-24 | Core | 7 | Not started | 0% | S09, S10 |  |  |  |  | ■ | ■
S13 | Software | Alerts view & privacy score | High-priority PII alert list and a transparent privacy score (shows how it is computed from blocked leaks and trackers). | Seeded PII leak raises an alert and changes the score | R4 | Ishak Palentino Napitupulu | R3 | 5 | 5 | 2026-10-24 | 2026-10-24 | Should | 4 | Not started | 0% | S08, S11 | [5 empty] | ■
S14 | Software | Geo-map (offline GeoIP + Leaflet) | Plot destination countries from an offline IP-to-location database. Do only if core features work end to end. | Map shows destinations from a test session | R4 | Ishak Palentino Napitupulu | R3 | 6 | 6 | 2026-10-25 | 2026-10-25 | Extended | 5 | Not started | 0% | S06 | [6 empty] | ■
S15 | Software | Certificate pinning & QUIC handling | Mark pinned apps as 'encrypted, not inspected' (host, size, process still logged). Script to block UDP 443 for the demo so browsers fall back to HTTP/2. | Pinned app shown correctly; browser traffic passes through the proxy after the script | R3 | Mahatma Brahmana | R2 | 5 | 5 | 2026-10-24 | 2026-10-24 | Should | 3 | Not started | 0% | S02 | [5 empty] | ■
S16 | Software | Anomaly flag (rule-based baseline) | Simple per-process baseline (e.g., a calculator opening a connection) raises an alert. IsolationForest only if time remains. | Test process outside its baseline is flagged | R3 | Mahatma Brahmana |  | 6 | 6 | 2026-10-25 | 2026-10-25 | Stretch | 3 | Not started | 0% | S04, S05 | [6 empty] | ■
S17 | Software | Automated tests (unit + integration) | Unit tests for Luhn, regex patterns, rule precedence and blocklist matching. Integration test using the local test server. | Test suite runs with one command and passes | R3 | Mahatma Brahmana | R2 | 5 | 6 | 2026-10-24 | 2026-10-25 | Core | 5 | Not started | 0% | S08, S09 | [5 empty] | ■ | ■
S18 | Software | Demo environment & seeded data | Local test server with a tracker-heavy page and a form with seeded dummy PII (dummy data only). Demo script with exact click path. | Demo script runs without internet access | R1 | Marcel Luther Sitorus | R2 | 4 | 5 | 2026-10-23 | 2026-10-24 | Core | 3 | Not started | 0% | S01 |  |  |  |  | ■ | ■
S19 | Software | End-to-end integration & bug fixing | Run the full flow: page load, tracker alert, PII halt, block, score update. Fix blockers only, no new features. | Full demo path works 3 times in a row | R2 | Audric Yusuf Maynard Simatupang | All | 6 | 6 | 2026-10-25 | 2026-10-25 | Core | 4 | In progress | 0% | S09-S13 | 2026-10-27 (Asia/Jakarta): Three real HTTP/HTTPS backend rehearsals pass for tracker Halt, PII allow/block, score, saved rules and timeout. Full dashboard rehearsal awaits R4 UI integration. | [5 empty] | ■
S20 | Software | KPI measurement, rehearsal & backup video | Measure targets: at least 90% flows attributed, 100% seeded PII detected, decision within 1 second. Rehearse demo and record a backup video. Take screenshots for the proposal. | KPI table with measured values; video file saved | R2 | Audric Yusuf Maynard Simatupang | R3, R4 | 7 | 7 | 2026-10-26 | 2026-10-26 | Core | 4 | In progress | 0% | S19 | 2026-10-27 (Asia/Jakarta): Measured Linux backend: 28/28 named flows, 18/18 PII matches, 23.17 ms maximum decision-to-response. Reproduce docs/evidence/kpis.json. Windows browser sample, real UI screenshots and backup video pending. | [6 empty] | ■
S21 | Software | Code freeze, cleanup & setup guide | Freeze the main branch, run linters, write the README with install, CA removal and demo steps. | Tagged release; README tested by a teammate | R1 | Marcel Luther Sitorus | R4 | 7 | 7 | 2026-10-26 | 2026-10-26 | Should | 2 | Not started | 0% | S19 | [7 empty] | ■
P01 | Proposal | Kickoff: outline, page budget & ownership | Map the official structure (Cover, Introduction, Problem Analysis, Proposed Solution, System Design, Technical Implementation, Expected MVP, References) to an outline. Page budget within the 15-page limit (cover, references, appendix excluded). Choose the writing tool, assign sections, set up an IEEE reference manager. | Outline with page budget and owner per section; shared document created | R1 | Marcel Luther Sitorus | All | 1 | 1 | 2026-10-20 | 2026-10-20 | Must | 3 | Not started | 0% |  |  | ■
P02 | Proposal | User validation: survey + interviews | The concept proposal has no user evidence, yet Problem & User Validation is 20% of the score. Launch a short survey (about 10 questions, target 30 or more responses from students, remote workers, SME staff) and run 3 to 5 short interviews. Close on Day 4. | Raw responses + summary charts + 3 to 5 interview notes | R1 | Marcel Luther Sitorus | R4 | 1 | 4 | 2026-10-20 | 2026-10-23 | Must | 5 | Not started | 0% |  |  | ■ | ■ | ■ | ■
P03 | Proposal | Cover page & placeholder cleanup | Fix the cover (title, team name Senklok, member names, institutions). Replace placeholders in the concept proposal such as [Team Name] and [Windows 11 / to be confirmed]. | Cover done; no placeholder text left | R4 | Ishak Palentino Napitupulu |  | 1 | 1 | 2026-10-20 | 2026-10-20 | Must | 1 | Not started | 0% | S01 |  | ■
P04 | Proposal | Introduction | Background with sourced data, Problem Identification (specific problem, causes, impacts) and 3 to 4 SMART objectives (use the KPIs: 90% attribution, 100% PII detection, decision within 1 s). | Section drafted, every statistic cited | R1 | Marcel Luther Sitorus | R3 | 2 | 2 | 2026-10-21 | 2026-10-21 | Must | 4 | Not started | 0% | P01 |  |  | ■
P05 | Proposal | Problem Analysis: root cause | Root-cause analysis with a fishbone diagram or 5-Whys: encrypted traffic, invisible per-app behavior, expert-only tools, lack of consent. | Diagram + 1 to 2 pages of text | R1 | Marcel Luther Sitorus | R3 | 2 | 3 | 2026-10-21 | 2026-10-22 | Must | 3 | Not started | 0% | P04 |  |  | ■ | ■
P06 | Proposal | Problem Analysis: existing solutions & opportunity | Compare existing tools (GlassWire, Little Snitch, Wireshark, mitmproxy and open-source firewalls such as OpenSnitch or Portmaster) with strengths, limits, gaps. Verify each tool's features on its official site. Derive the opportunity. | Comparison table + opportunity statement | R3 | Mahatma Brahmana | R1 | 2 | 3 | 2026-10-21 | 2026-10-22 | Must | 4 | Not started | 0% | P01 |  |  | ■ | ■
P07 | Proposal | Proposed Solution section | Solution overview, main features and roles, workflow (input to output), key innovations versus existing tools (reuse and extend Table I of the concept proposal). | Section drafted with workflow figure reference | R1 | Marcel Luther Sitorus | R2 | 3 | 4 | 2026-10-22 | 2026-10-23 | Must | 5 | Not started | 0% | P06 |  |  |  | ■ | ■
P08 | Proposal | System Design diagrams | System architecture, Halt workflow flowchart/sequence, use-case diagram, database ERD (flows, rules, alerts, blocklist, settings) and an API endpoint table. Use real names from the code. | 5 clean diagrams exported as images | R4 | Ishak Palentino Napitupulu | R2, R3 | 3 | 5 | 2026-10-22 | 2026-10-24 | Must | 7 | Not started | 0% | S05, S06 |  |  |  | ■ | ■ | ■
P09 | Proposal | Technical Implementation section | Stack with justification per layer, module breakdown, security-by-design measures, testing approach, feasibility evidence (prototype screenshots from Days 2 to 4), legal and ethical use (own device only, CA consent). | Section drafted with at least 2 real screenshots | R3 | Mahatma Brahmana | R2 | 4 | 5 | 2026-10-23 | 2026-10-24 | Must | 5 | Not started | 0% | S02, S04 |  |  |  |  | ■ | ■
P10 | Proposal | Expected MVP + impact, sustainability & dev plan | The official structure has no separate impact or plan section, but both are scored (15% each). Put them here: MVP features and KPIs, measurable impact, scalability and long-term use, timeline to Final Round, resources, risk table. | Section drafted with MVP table, timeline and risks | R1 | Marcel Luther Sitorus | All | 5 | 5 | 2026-10-24 | 2026-10-24 | Must | 5 | Not started | 0% | P07 | [5 empty] | ■
P11 | Proposal | Integrate user-validation results | Add survey and interview findings (counts, percentages, quotes) to Background, Problem Identification and Opportunity. | Evidence visible in at least 2 sections | R1 | Marcel Luther Sitorus | R4 | 5 | 5 | 2026-10-24 | 2026-10-24 | Must | 2 | Not started | 0% | P02 | [5 empty] | ■
P12 | Proposal | References (IEEE) & fact-check | Check every cited number and source (e.g., IBM report figures, PP 33/2026), convert to IEEE format, number by order of first appearance. | Every in-text citation matches a verified reference | R1 | Marcel Luther Sitorus | R3 | 5 | 6 | 2026-10-24 | 2026-10-25 | Must | 3 | Not started | 0% | P04-P10 | [5 empty] | ■ | ■
P13 | Proposal | Assemble full draft & format | Merge all sections, consistent figure and table numbering, English only, no SARA content, within 15 pages (excluding cover, references, appendix). Make diagram text legible. | Single PDF draft within the page limit | R4 | Ishak Palentino Napitupulu | R1 | 5 | 6 | 2026-10-24 | 2026-10-25 | Must | 4 | Not started | 0% | P04-P12 | [5 empty] | ■ | ■
P14 | Proposal | Peer review against scoring rubric | Each reviewer scores the draft on the 5 criteria (Problem 20, Solution 25, Technical 25, Impact 15, Plan 15) and lists the top fixes. | Review sheet with scores and fix list | R2 | Audric Yusuf Maynard Simatupang | All | 6 | 6 | 2026-10-25 | 2026-10-25 | Must | 3 | In progress | 0% | P13 | 2026-10-27 (Asia/Jakarta): Completed preliminary-PDF rubric review: internal 62/100 with prioritized fixes in docs/proposal/audric-peer-review.md. Final P14 acceptance awaits the P13 assembled full draft. | [5 empty] | ■
P15 | Proposal | Final revision, PDF export & submission | Apply fixes, export as FPH_Senklok.pdf, check page count, fonts, figures and links, submit before the deadline and keep a backup copy. | Submission confirmed | R1 | Marcel Luther Sitorus | R4 | 7 | 7 | 2026-10-26 | 2026-10-26 | Must | 3 | Not started | 0% | P14 | [7 empty] | ■
Formulas:
Start date = Setup!$B4+[Start day]-1
Due date = Setup!$B4+[Due day]-1

## Setup
SentriFlow 7-Day Tracker: Setup
Edit the yellow cells. Everything else recalculates.
Day 1 start date | 2026-10-20 | Assumption: Day 1 = today (20 Oct 2026). Change if your 7-day window starts elsewhere.
Available hours per person per day | 6 | Assumption: 6 h/day per member. Adjust to real availability alongside other courses.
Team roles (role codes are used in the Tasks sheet)
Role code | Name | Focus
R1 | Marcel Luther Sitorus | Project lead, proposal writing, user validation, demo data
R2 | Audric Yusuf Maynard Simatupang | Proxy, backend, Halt engine, integration
R3 | Mahatma Brahmana | Process mapping, inspector, blocklist, database, tests
R4 | Ishak Palentino Napitupulu | Frontend dashboard, diagrams, proposal formatting
Assumption: the mapping of members to roles is my suggestion (names taken from the cover of CP_Senklok.pdf). Swap names freely.
Status values | Progress counted
Not started | 0%
In progress | 50%
Blocked | 0%
Done | 100%
Priority values
Core
Must
Should
Extended
Stretch
How to use: update only the Status column (and Notes) in the Tasks sheet. % done, dates, Gantt bars and the Dashboard update automatically. Extended and Stretch tasks are the first to cut if the Day-4 checkpoint is missed.